## 90-day plan
90-day rollout plan
A rollout plan for an employee survey or workforce performance platform. Edit tasks, owners and dates.
Week | Phase | Task | Owner | Due | Status | Notes
1 | Set up | Agree the 1 or 2 decisions the results will inform
1 | Set up | Name an owner and a sponsor
1 | Set up | Sign the data processing agreement
2 | Set up | Load employees: HR system sync or file
2 | Set up | Set up single sign-on, if used
2 | Set up | Agree the minimum group size for results
3 | Set up | Map teams and managers
3 | Set up | Choose languages for employees and managers
4 | Prepare | Brief managers: what is asked, when results arrive, what they will do
4 | Prepare | Test the survey with a small group
5 | Prepare | Send the announcement
6 | Run | Open the survey
6 | Run | Make sure people without email or a desk can answer
7 | Run | Send reminder halfway
8 | Run | Send last reminder; close the survey
9 | Results | Share overall results with everyone
9 | Results | Give managers their team results
10 | Act | Each team picks 1 to 3 actions
11 | Act | Actions written down with owners and dates
13 | Review | Progress update to all employees
13 | Review | Review the rollout: what to change next time
Done
Free template from workforceperformanceplatform.com/free-downloads · Published by thrive at work